## Sheet1
PROJECT NUMBER |  | 22
PROJECT NAME |  | Plugin for Ontology extraction
PROJECT MENTOR (sponsor) |  | Lalit Mohan
TEAM MEMBERS |  | Anirudha Ramesh | Saujas Srinivasa Vaduguru | Shikhar Shasya
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments
WEEK 1 ( August 7- August 13 )
Fix first meeting with client | Coordination | Saujas | 0.3 | 0.2 | Done
Get familiar with Ontology | Preparation | All | 1.5 | 2 | Done
Use pizza and wine ontologies to explore about protege | Preparation | All | 2 | 1.5 | Done
Install and set up WebProtege | Preparation | All | 1 | 1.5 | Done
Experiment with Ontographs | Preparation | All | 3 | 3 | Done
Explore how to add plugins to WebProtege | Preparation | All | 3 | 3 | Done
WEEK 2 ( August 14 - August 20 )
GIT Repository setup | Preparation | Anirudha | 0.3 | 0.3 | Done
Find a way to integrate ontograf with web protege | Preparation | All | 3 | 3 | Not Done | WebVOWL was used instead
Explore WebVOWL as an option and compare with protege | Preparation | All | 3 | 3 | Done | WebVOWL was used instead of protege
Document first Team meeting, first TA meeting, 2 client meetings | Documentation | Anirudha | 2 | 2 | Done
Upload Status Tracker version1 | Documentation | Saujas | 0.3 | 0.3 | Done
Upload Project Synopsis version1 | Documentation | Shikhar | 1.5 | 2 | Done
WEEK 3 ( August 21 - August 27 )
Decide technical requirements for using WebVOWL | Preparation | All | 1 | 1 | Done
Document Third Client Meeting | Documentation | Shikhar | 0.3 | 0.3 | Done
UI for accepting/rejecting new concepts/relationships | Preparation | Anirudha | 3 | 3 | Done
Set up the backend using Flask framework that serves WebVOWL | Preparation | Saujas, Shikhar | 3 | 4 | Done
WEEK 4 ( August 28 - September 3 )
Upload SRS Document after consultation with client | Preparation | Shikhar | 4 | 3 | Done
Set up basic accept / reject functionality | Preparation | Anirudha | 5 | - | Pending | Partially working
Document 4th Client Meeting | Documentation | Anirudha | 0.3 | - | Pending | Documentation completed next week
WEEK 5 ( September 8 - September 15 )
Document 4th Client Meeting | Documentation | Anirudha | 0.3 | 0.3 | Done
Document 2nd Team Meeting | Documentation | Anirudha | 0.3 | 0.3 | Done
Creation of Database | Preparation | Saujas | 5 | 5 | Done
Asynchronous accept/reject functionality | Continuation | Anirudha | 3 | 3 | Done | Fully Working
WEEK 6 ( September 16 - September 22 )
Upload Project Plan version1 | Documentation | Shikhar | 1.5 | 1.5 | Done
Identify new nodes added to the existing ontology | Preparation | Saujas,Shikhar | 5