## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 22
PROJECT NAME | Protege Plugin for Ontology Extraction
PROJECT MENTOR (sponsor) | Lalit Mohan S.
TEAM MEMBERS | Anirudha Ramesh
Saujas Srinivasa Vaduguru
Shikhar Shasya

## Status
PROJECT NUMBER | 22
PROJECT NAME | Protege Plugin for Ontology Extraction
PROJECT MENTOR (sponsor) | Lalit Mohan S.
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (August 8- August 15)
Fix meeting with client | Coordination | Saujas | 0.15 | 0.15 | Done |  | 0 | 0
Get familiar with ontology | Preparation | All | 6 | 6 | Done |  | 0 | 0
Install, set up, and explore WebProtege | Preparation | All | 9 | 12 | Done | Installed both Web and Desktop Protege | -3 | 25
Fix meeting with TA | Coordination | Anirudha | 1 | 1 | Done
Week 2 (August 14 - August 20)
Explore WebVOWL | Preparation | All | 6 |  | Ongoing
Explore OntoGraf integration into WebProtege | Preparation | All | 3 |  | Ongoing
Set up Git Repository | Preparation | Anirudha | 0.5 | 1 | Done |  | -0.5 | 50
Update Minutes of Meetings | Coordination | Anirudha | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Saujas | 0.5 |  | Done
Week 3 (August 21 - August 27)
Week 4 (August 28 - September 3)
Week 5
Week 6