## Sheet1
PROJECT NUMBER |  | 22
PROJECT NAME |  | Plugin for Ontology extraction
PROJECT MENTOR (sponsor) |  | Lalit Mohan
TEAM MEMBERS |  | Anirudha Ramesh | Saujas Srinivasa Vaduguru | Shikhar Shasya
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments
WEEK 1 ( August 7- August 13 )
Fix first meeting with client | Coordination | Saujas | 0.5 | 0.5 | Done
Get familiar with Ontology | Preparation | All | 1.5 | 2 | Done
Use pizza and wine ontologies to explore about protege | Preparation | All | 2 | 1.5 | Done
Install and set up WebProtege | Preparation | All | 1 | 1.5 | Done
Experiment with Ontographs | Preparation | All | 3 | 3 | Done
Explore how to add plugins to WebProtege | Preparation | All | 3 | 3 | Done
WEEK 2 ( August 14 - August 20 )
GIT Repository setup | Preparation | Anirudha | 0.5 | 0.5 | Done
Find a way to integrate ontograf with web protege | Preparation | All | 3 | 3 | Not Done | WebVOWL was used instead
Explore WebVOWL as an option and compare with protege | Preparation | All | 3 | 3 | Done | WebVOWL was used instead of protege
Document first Team meeting, first TA meeting, 2 client meetings | Documentation | Anirudha | 2 | 2 | Done
Upload Status Tracker version1 | Documentation | Saujas | 1 | 1 | Done
Upload Project Synopsis version1 | Documentation | Shikhar | 1.5 | 2 | Done
WEEK 3 ( August 21 - August 27 )
Decide technical requirements for using WebVOWL | Preparation | All | 1 | 1 | Done
Document Third Client Meeting | Documentation | Shikhar | 0.5 | 0.5 | Done
UI for accepting/rejecting new concepts/relationships | Preparation | Anirudha | 2 | 2 | Done
Set up the backend using Flask framework that serves WebVOWL | Preparation | Saujas, Shikhar | 3 | 4 | Pending | Completed later in the following weeks
WEEK 4 ( August 28 - September 3 )
Upload SRS Document after consultation with client | Preparation | Shikhar, Saujas | 4 | 3 | Done
Set up basic accept / reject functionality | Preparation | Anirudha | 5 | 6 | Pending | Partially working
Document 4th Client Meeting | Documentation | Anirudha | 0.5 | - | Pending | Documentation completed next week
WEEK 5 ( September 8 - September 15 )
Document 4th Client Meeting and 2nd Team meeting | Documentation | Anirudha | 1 | 1 | Done
Asynchronous accept/reject functionality | Continuation | Anirudha | 3 | 3 | Done | Fully Working
Database creation to store nodes, user information | Preparation | All | 3 | 3 | Done
WEEK 6 ( September 16 - September 22 )
Upload Project Plan version1 | Documentation | Shikhar | 2 | 2 | Done
Continue backend work for storing decisions, and sending new relations | Preparation | Saujas | 5 | 5 | Done
Updation of Status Tracker | Continuation | Shikhar | 2 | 2 | Done
Document 5th client meeting | Documentation | Anirudha | 0.5 | 0.5 | Done
Disable all existing methods of file upload, and integrate file upload with the visualization software | Preparation | Anirudha | 4 | 5 | Done
WEEK 7 ( September 23 - September 29)
Upload Test Plan | Documentation | Anirudha | 2 | 2 | Done
Display accept/reject option only for relationships present in the graph | Preparation | Shikhar | 6 | 7 | Pending
Change color for the new relations | Preparation | Anirudha | 8 | 12 | Done
Complete storing decisions for a single user | Preparation | Saujas | 10 | 12 | Pending
Document 6th client meeting | Documentation | Anirudha | 0.5 | 0.5 | Done
WEEK 8 ( September 30 - October 6 )
Store accept/reject decisions in the database for a single user | Continuation | Saujas | 3 | 4 | Done
Integrate storing decisions for single user | Continuation | Anirudha | 2 | 4 | Done
Display accept/reject option only for relationships present in the graph | Continuation | Shikhar | 4 | 5 | Done
Updation of Status Tracker | Continuation | Shikhar | 2 | 2 | Done
Making presentation and video for R1 | Preparation | All | 4 | 5 | Done
WEEK 9 ( October 24 - October 31 )
Upload Design Document version1 | Preparation | Anirudha | 1 | 1 | Done
Understand the basics of owl api for writing back to the owl file | Preparation | Shikhar | 3 | 3 | Pending | Completed next week
Add concepts, accept/reject concpets to database | Preparation | Saujas | 2 | 2 | Done
Expanded accept/reject to classes and color the new classes | Preparation | Anirudha | 3 | 4 | Done
WEEK 10 ( November 2 - November 9 )
Implement delete functionality for classes, restrictions and subclass axioms using owlapi | Continuation | Shikhar | 15 | 20 | Done
Google Authentication for users | Preparation | Saujas | 3 | 4 | Done
Limited accept/reject to only new relations/nodes once per user per access of a particular ontology | Preparation | Anirudha | 3 | 4 | Done
Deployment of the project | Preparation | Saujas, Anirudha | 6 | 6 | Done
Making presentation and video for R2 | Preparation | All | 4 | 4 | Done